## Sheet1
task | start | end
paper research | 2023-09-04 | 2023-10-01
implementation research and prototyping | 2023-10-02 | 2023-11-26
study design research | 2023-10-23 | 2023-11-05
proposal writing | 2023-11-06 | 2023-11-19
proposal improvement | 2023-11-20 | 2023-11-26
create app design | 2023-11-20 | 2023-12-03
create app structure | 2023-11-20 | 2023-12-03
Implementation of rough app structure | 2023-11-27 | 2023-12-03
Implementation of real-time contact detection | 2023-12-04 | 2023-12-17
Implementation of Interventions | 2023-12-11 | 2023-12-24
Implementation of background running | 2023-12-25 | 2024-01-07
Implementation of data collection | 2024-01-01 | 2024-01-14
internal test run and improvement | 2024-01-08 | 2024-01-21
Implementation of questionnaires (?)
create questionnaires | 2024-01-01 | 2024-01-07
recruit test subjects (advertisment, etc.) | 2024-01-15 | 2024-03-03
execute study (incl. meetings for final feedback) | 2024-01-29 | 2024-03-17
write about final implemetation (incl. problems?) | 2024-01-29 | 2024-03-17
evaluate study results | 2024-03-18 | 2024-03-31
write about study results (correspond with rq) | 2024-03-25 | 2024-04-07
improvement of thesis | 2024-04-01 | 2024-04-14
delivery of thesis | 2024-04-15 | 2024-04-21
research
implementation
study
ba. thesis
research
implementation
study
ba. thesis